| PEDAGOGICAL BASES | #### T&T |
| --- | --- |
| ###### Regular dialog between RMF ###### and each road authority 1/3 | ###### 5.4 |

The Road Authority

(the network owner)

The RMF

(the “local donor”)

## 1. The programming process

## Pre-budgeting

notification of the annual draft budget pre-allocation, based on a low revenue hypothesis and    the allocation key

## Programming

Draft prioritized program: studies / works / work control / network monitoring
(N.B. annual program for authorization + 3-year program for information only)

## Program authorization

Clearance for launching the program; and possibly: payment proxy    limited    to small contracts (non-transferable proxy, with ceiling)

## Procurement follow-up

transmission of draft contracts for clearance

OR contracts for information

depending on the evolution of the revenue or on the balance of the reserve for emergency works.

Similar but shortened process to Step 1 above.

## 1 bis . Possibly: Additional programming process at mid-year

| PEDAGOGICAL BASES | #### T&T |
| --- | --- |
| ###### Regular dialog between RMF ###### and each road authority 2/3 | ###### 5.4 |

The Road Authority

(the network owner)

The RMF

(the “local donor”)

## 2. Program    implementation

## Monthly monitoring data set

for program follow-up

(administrative / physical / accounts)

## First clearance for payments to be performed by RMF

for large contracts

Possibly: state of small payments already performed by the road authority by proxy for small contracts

## State of payments

performed by RMF on large contracts

Final discharge for small payments performed by the road authority by proxy on small contracts

## Final monitoring data set

about the satisfactory completion of the program and commitments’ closure, with recap of commitments to be carried forward  (pluriannual contracts)

Including : various performance indicators (range of payment times, range of work time overruns, etc.)

| PEDAGOGICAL BASES | #### T&T |
| --- | --- |
| ###### Regular dialog between RMF ###### and each road authority 3/3 | ###### 5.4 |

The Road Authority

(the network owner)

The RMF

(the “local donor”)

## 3. Program    monitoring

## Random sampling or

## serious suspicious cases:

Technical audit on works without interfering with the regular

control of the contractor

## Random sampling/

## suspicious cases:

Participating, as an observer, in commissions responsible for provisional or final work acceptance

Systematically:
a posteriori audit of program implementation

## In case of proven mismanagement:

- conservatory suspension of all or part of the allocation as yet unspent ?

- formal notice to end or suspend temporarily implementation of incriminated contracts

- making a claim before administrative and/or penal tribunals

- conservatory cancellation of individual proxy for small payments

## Yearly macro-indicators

## of network performance :

Levels of traffic / standard traffic-flow speeds    (for example from indicator SOURCE) / etc.